## Sheet1
Date | Tasks to Accomplish
Jan 1-15 | Database setup and backend development
Jan 16-31 | Frontend development
Feb 1-15 | Implement user authentication and authorization
Feb 16-28 | Job listing functionality and application features
Mar 1-15 | Testing and debugging, fix any issues
Mar 16-31 | Website optimization and performance tuning
Apr 1-15 | Final preparations for launch, marketing strategy
Apr 16-30 | Launch website, monitor and address initial feedback
May 1-15 | Ongoing monitoring, updates, and improvements
May 16-31 | Evaluate performance, gather user feedback